## Sheet1
| Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Week 21 |  |  |  |  | Week 22 |  |  |  |  | Week 23 |  |  |  |  | Week 24 |  |  |  |  | Week 25 |  |  |  |  | Week 26 |  |  |  |  | Week 27 |  |  |  |  | Week 28
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140
Idententification and gathering of requirements
Analysation of the requirements
Define Project Scope
Develop Project Plan
Team formation and role definition
Initial sprint planning
Milestone: Product defined
Implement Login Interface
Develop login system
Design and implement signup forms
Milestone: Login Done
Create "Forgot Password" functionality
Desgin UI for the guest user mode
Develop guest user access system
Implement time-based learning modules system
Implement live streaming feature for teachers
Design and implement assignment distribution
Develop system for detecting and visualizing equations
Revise the module as required
Milestone: Learning Modules Done
Create AR field trip system for user access
Develop user interface for selecting and joining AR field trips
Design UI for teachers to upload 3D videos
Develop the feature for teachers to upload videos
Milestone: AR field trips Done
Implement natural language interface
Develop real-time translation capabilities
Create predefined lists of languages for selection
Milestone: NLP Done
Develop student monitoring dashboard
Implement holographic communication feature
Develop content creation hub
Milestone: Student Monitoring Done
Design UI for students to simulate experiments
Implement virtual environment simulation
Develop functionality for saving simulated data
Create evaluation system for teachers in virtual labs
Milestone: Virtual Labs Simulation Done
System integration testing
Regression testing
Fixing Bugs
Acceptance testing
Milestone: Testing Done
Creating user manuals and Guidelines
Technical Documentation
Milestone: Documentation complete
Deployment planning
Deoployment Management co-ordination
Deployment verification
Delivery of the system
Monitoring of the performance
Milestone: Project Complete
Task : Person
Weeks