## Sheet1
Risks | Category | Probability | Impact | RMMM
Size estimate may be significantly low | PS | 50% | 2 | Revisit size estimation due to potential significant underestimation
Larger number of users than planned | PS | 20% | 2 | Adjust project scalability strategy to accommodate the unexpected increase in user volume.
Less reuse than planned | PS | 60% | 3 | Revise reuse strategy and explore alternative approaches to maximize resource utilization
Resistance from end-users | BU | 50% | 2 | Train the users to use this new technology.
Tightened delivery deadline | BU | 40% | 3 | Prioritize must have feature development to accelarate development
Loss of funding | CU | 40% | 1 | Hold frequent meeting with shareholders to show them the value they will get from funding
Changing customer requirements | PS | 70% | 3 | Follow agile practices to be ready to accommodate quick changes
Technology not meeting expectations | TE | 40% | 2 | Import advanced technology to meet expected quality or custom build from China
Lack of training on developement tools | DE | 80% | 1 | Prepare documentation and training materials for the development tools
Inexperienced staff | ST | 50% | 2 | Train the staff with new technologies.
High staff turnover | ST | 50% | 2 | Implement knowledge transfer mechanisms to mitigate the impact of high staff turnover on project continuity
Hardware might malfunction | DE | 10% | 1 | Incorporate redundancy measures and establish contingency plans to address potential hardware malfunctions
Connectivity issues | DE | 25% | 3 | Develop backup communication protocols and establish troubleshooting procedures to mitigate potential connectivity issues
Insufficient battery life | DE | 10% | 2 | Implement power management strategies and provide contingency plans for addressing instances of insufficient battery life
Lack of user training | CU | 30% | 2 | Develop comprehensive user training programs and provide ongoing support to mitigate the impact of a lack of user training
Physical safety hazards | CU | 15% | 1 | Conduct regular safety inspections and implement precautionary measures to mitigate potential physical safety hazards
Incompatibility with existing infrastruture | TE | 40% | 2 | Perform thorough compatibility testing and establish migration strategies to address any incompatibility issues with existing infrastructure
High production costs | BU | 30% | 2 | Optimize resource allocation and explore cost-saving measures to mitigate the impact of high production costs
Delays in developing or manufacturing | PR | 25% | 2 | Implement agile project management techniques and establish contingency plans to address delays in development or manufacturing